## Table 1
2007-398-00 YAKIMA TRIBUTARY ACCESS & HABITAT PROGRAM (YTAHP) Project Planning & Prioritization | [14 empty] | Total Metrics | 32 | 3 | 3480 | 128 | 19683 |  | 14720000
[14 empty] | Planning & Construction Totals Planning Only Totals (gray italicized text) |  | 27.18 | 3 | 3480 | 69 | 13319 |  | 10320000
[16 empty] | 4.78 | 0 | 0 | 59 | 6364 |  | 4100000
Prioritization | Proposed Project Name | Planning Year | Implementation Year (Calendar) | Subbasin | Tributary | Reach (if identified) | Latitude (decimal/ degrees) | Longitude (decimal/ degrees) | Target/ Focal Species | Life History (LH) Stages Present (egg/juvenile/ rearing/ spawning/holding) | Limiting Factors (LF) Identified | Project Description | Work Elements | Describe How Project Addresses LF | Anticipated Benefit (complexity, refugia, etc.) | Anticipated miles of habitat opened | Anticipated acres of riparian or floodplain enhanced | Anticipated feet of stream enhanced | Anticipated CFS Screened | Anticipated Acre-Feet Screened | Landowner (Private, USFS, BLM, etc.) | Estimated Cost (Design/ Implementation) | Cost Share Available
North Yakima Conservation District
| Cowiche MSA | [14 empty] | 11.2 | 0 | 0 | 0 | 0 |  | 400000
1 | Cowiche Mouth Barrier Removal | 2026 | 2027 | Cowiche MSA | Cowiche Creek |  | 46.6278 | -120.5689 | Mid-Columbia Steelhead, coho, Chinook salmon | egg/juvenile/ rearing/ spawning | Habitat Quantity - Anthropogenic Barriers | Removal of dam at mouth of Cowiche Creek. Irrigation withdraw will be switched to Nelson Dam upstream allowing for removal of structure. | 175-Produce Design 165-Produce Environmental Compliance Documentation 184-Install Fish Passage Structure | Barrier removal will improve available habitat to rearing fish during the summer, as well as provide better passage for migrating adults | Increased habitat availability | 1.2 |  |  |  |  | Yakima County | 250000 | Maybe- City of Yakima, Yakima County
2 | Garretson Diversion Removal | 2028 | 2029 | Cowiche MSA | Cowiche Creek |  | 46.625 | -120.5839 | Mid-Columbia Steelhead, coho, Chinook salmon | egg/juvenile/ rearing/ spawning | Habitat Quantity - Anthropogenic Barriers | Removal of abandoned gravity diversion | 175-Produce Design 165-Produce Environmental Compliance Documentation 184-Install Fish Passage Structure | Barrier removal will improve available habitat to rearing fish during the summer, as well as provide better passage for migrating adults | Increased habitat availability | 10 |  |  |  |  | City of Yakima/ private diversion | 150000 | Maybe- City of Yakima
| Wenas MSA | [14 empty] | 9 | 1 | 2150 | 24.76 | 4303 |  | 3440000
1 | Hass | 2026/2027 | 2028 | Wenas MSA | Wenas Creek |  | 46.7733 | -120.629 | Mid-Columbia Steelhead | egg/juvenile/ rearing/ spawning | Passage, screening, water quality, water quantity | The project focuses on restoring fish passage, installing a compliant fish screen at two diversions, The diversions will be equipped with a WDFW and NMFS compliant fish screen to prevent entrainment of Mid-Columbia steelhead. A grade control structure will be implemented to provide passage. | 175-Produce Design 165-Produce Environmental Compliance Documentation 85-Remove/Breach Fish Passage Barrier 184-Install Fish Passage Structure 208-Irrigation Infrastructure Construction or Replacement 47-Plant Vegetation 198-Maintain Vegetation | Screening of gravity diversion will eliminate fish mortality and injury through entrainment , Barrier removal will improve available habitat to rearing fish during the summer, as well as provide better passage for migrating adults. | Increased habitat availability and potential water quantity for instream benefit | 5 |  |  | 4 | 300 | Private | 500000 | Yes- WSCC
2 | Wenas Irrigation District | 2027 | 2028 | Wenas MSA | Wenas Creek |  | 46.7819 | -120.6433 | Mid-Columbia Steelhead | egg/juvenile/ rearing/ spawning | Habitat Quantity - Anthropogenic Barriers | The project focuses on providing passage and water measurement at the WID diversion, which diverts water from NF Wenas Creek down SF Wenas Creek to and consists of a two sided check dam that diverts flow and creates a 1.5 ft. drop in water surface elevation; | 175-Produce Design 165-Produce Environmental Compliance Documentation 85-Remove/Breach Fish Passage Barrier 184-Install Fish Passage Structure 208-Irrigation Infrastructure Construction or Replacement 47-Plant Vegetation 198-Maintain Vegetation | Barrier removal will improve available habitat to rearing fish during the summer, as well as provide better passage for migrating adults. | Increased habitat availability and potential water quantity for instream benefit | 2 |  |  |  |  | Private | 2000000 | Maybe- WSCC
3 | SF Wenas BR | 2027 | 2028 | Wenas MSA | Wenas Creek |  | 46.8082 | -120.6605 | Mid-Columbia Steelhead | egg/juvenile/ rearing/ spawning | Habitat Quantity - Anthropogenic Barriers | Removal of irrigation diversion to provide fish passage | Remove/Breach Fish Passage Barrier | Barrier removal will improve available habitat to rearing fish during the summer, as well as provide better passage for migrating adults. | Increased habitat availability and potential water quantity for instream benefi. | 1 |  |  |  |  | Private | 30000 | no
4 | Robertson Diversion | 2028 | 2029 | Wenas MSA | Wenas Creek |  | 46.737 | -120.6016 | Mid-Columbia Steelhead | egg/juvenile/ rearing/ spawning | Injury and Mortality - Mechanical Injury | Implementation of a fish screen and pump on Wenas Creek to remove irrigator off of shared gravity diversion and improve on-farm irrigation use. This will be part of a larger project to address the gravity diversion and find alternative means for all irrigators to get water with the goal of removing the gravity diversion and associated fish passage barrier | 175-Produce Design 165-Produce Environmental Compliance Documentation 208-Irrigation Infrastructure Construction or Replacement | Compliant fish screen to prevent fish mortality and injury through entrainment and impingement. Irrigation efficiencies improvments will increase available water instream. | Increase in available habitat and fish protection | 4 |  |  | 0.79 | 158 | Private | 30000
4 | Sisk Rd. Diversion | 2029 | 2030 | Wenas MSA | Wenas Creek |  | 46.7859 | -120.6445 | Mid-Columbia Steelhead | egg/juvenile/ rearing/ spawning | Injury and Mortality - Mechanical Injury | Implementation of a fish screen and pump station on Wenas Creek to remove irrigator off of shared gravity diversion. | 175-Produce Design 165-Produce Environmental Compliance Documentation 208-Irrigation Infrastructure Construction or Replacement | Compliant fish screen to prevent fish mortality and injury through entrainment and impingement. Irrigation efficiencies improvments will increase available water instream. | Increase in available habitat and fish protection | 4 |  |  | 0.6 | 50 | Private | 50000
6 | Wenas Creek Pump Screen (Wilson) | 2028 | 2029 | Wenas MSA | Wenas Creek |  | 46.7189 | -120.5724 | Mid-Columbia Steelhead | egg/juvenile/ rearing/ spawning | Injury and Mortality - Mechanical Injury | Installation of compliant fish screen on pump diversion | 208-Irrigation Infrastructure Construction or Replacement | Compliant fish screen to prevent fish mortality and injury through entrainment and impingement. Irrigation efficiencies improvments will increase | Increase in available habitat and fish protection |  |  |  | 0.13 | 73 | Private | 10000 | Maybe-Mitchell Act Funds
7 | Wenas Creek Pump Screen (Adobe Rd.) | 2029 | 2030 | Wenas MSA | Wenas Creek |  | 46.71 | -120.528 | Mid-Columbia Steelhead | egg/juvenile/ rearing/ spawning | Injury and Mortality - Mechanical Injury | Installation of compliant fish screen on pump diversion | 208-Irrigation Infrastructure Construction or Replacement | Compliant fish screen to prevent fish mortality and injury through entrainment and impingement. Irrigation efficiencies improvments will increase | Increase in available habitat and fish protection |  |  |  | 0.09 | 24 | Private | 10000 | Maybe-Mitchell Act Funds
Kittitas County Conservation District
| Caribou MSA | [14 empty] | 6.8 | 0.6 | 450 | 40.2 | 5259.9 |  | 4500000
1 | Cooke Creek 04.3 - Screen & Passage | 2025 | 2026 | Caribou MSA | Cooke Creek | 2 - Between EWC and CID | 46.9827 | -120.4234 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Gibb diversion just downstream of John Wayne Trail - screening, passage and potential on-farm sprinkler conversion to increase water use efficiency and reduced sediment/nutrient transport to stream | 175-Produce Design 165-Produce Environmental Compliance Documentation 184-Install Fish Passage Structure 208-Irrigation Infrastructure Construction or Replacement 47-Plant Vegetation 198-Maintain Vegetation | Installs compliant fish screen to prevent fish mortality and injury Corrects fish passage barrier to increase available habitat | Increase in available habitat and Protection from mechanical injury | 0.36 | 0.2 | 150 | 5 | 1950 | Private | 350000 | Maybe - USDA RCPP
2 | Cooke Creek 03.5 - Fairview to Palouse to Cascades Screen & Passage | 2025 | 2026 | Caribou MSA | Cooke Creek | 2 - Between EWC and CID | 46.9789 | -120.4295 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Assess 0.75 stream miles of Cooke Creek to locate multiple small pump diversions and provide screens and to inventory any passage barriers. | 115- Produce Inventory or Assessment 175-Produce Design 165-Produce Environmental Compliance Documentation 208-Irrigation Infrastructure Construction or Replacement | Installs compliant fish screen to prevent fish mortality and injury Corrects fish passage barrier to increase available habitat | Increase in available habitat and Protection from mechanical injury | 0.9 |  |  | 1.5 | 585 | Private | 45000 | Maybe - USDA RCPP
3 | Cooke Creek 02.27 - Tjossem Road fish passage | 2027 | 2030 | Caribou MSA | Cooke Creek | 1 - EWC and downstream | 46.9634 | -120.4512 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers | Assess the irrigation diversion for passability and design and install fish passage structures to address barrier status. | 175-Produce Design 165-Produce Environmental Compliance Documentation 184-Install Fish Passage Structure | Corrects Fish Passage to increase available habitat | Increase in available habitat | 1.2 |  |  |  |  | Private | 85000
4 | Parke Creek 0.46 | 2027 | 2028 | Caribou MSA | Parke | 1 - EWC and downstream | 46.9448 | -120.4664 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers | Assess bridge/culvert structure for passibilty. Previous project relocated diversions and check boards no longer used, but passage may still be an issue. | 175-Produce Design 165-Produce Environmental Compliance Documentation 184-Install Fish Passage Structure | Corrects fish passage barrier to increase available habitat | Increase in available habitat | 0.5 | 0.2 | 150 |  |  | Private | 65000
5 | Caribou Creek 03.37 Pump Diversion | 2027 | 2028 | Caribou MSA | Caribou Creek | 2 - Between EWC and CID | 46.9759 | -120.4188 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Injury and Mortality - Mechanical Injury | Screen for small pump irrigating 12-15 acres of pasture to west of the creek | 175-Produce Design 165-Produce Environmental Compliance Documentation 208-Irrigation Infrastructure Construction or Replacement | Install compliant fish screen to prevent fish mortality and injury through entrainment and impingement | Protection from mechanical injury |  |  |  | 0.5 | 195 | Private | 5000
6 | Caribou Creek 03.9 (at John Wayne Trail) | 2035 | 2036 | Caribou MSA | Caribou Creek | 2 - Between EWC and CID | 46.9759 | -120.4188 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Screening and passage planning and implementation for gravity diversion [WR S4-84421-J] irrigating 62 acres. | 175-Produce Design 165-Produce Environmental Compliance Documentation 184-Install Fish Passage Structure 208-Irrigation Infrastructure Construction or Replacement | Install compliant fish screen to prevent fish mortality and injury through entrainment and impingement | Increase in available habitat and Protection from mechanical injury | 0.4 | 0.2 | 150 | 0.8 | 312 | Private | 300000 | Maybe - USDA RCPP
7 | Caribou Creek 04.3 - Cascade Irrigation District | 2023-2025 |  | Caribou MSA | Caribou Creek | 2 - Between EWC and CID | 46.9845 | -120.4087 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Cascade Irrigation District intersection with Caribou Creek and diversion of water right S4-84625-J. Design work has been ongoing at this site since 2017 along with their Currier Creek and Coleman Intersections. Projects involve siphon for canal under creek and diversion with fish screen and fishway. | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structures for implementation | Increase in available habitat and Protection from mechanical injury | 1 |  |  | 30 | 1255 | Irrigation District ROW | 2100000 | Yes - Salmon Recovery Funding Board for design
8 | Caribou Creek 05.3 Screening and Passage | 2027 |  | Caribou MSA | Caribou Creek | 3- Between CID and KRD | 46.9944 | -120.3974 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Plan and design fish screen and fish passage for diversion of 0.5 CFS [Water Right S4-84535-J] for irrigation of 20 acres and stock water and potential on-farm sprinkler conversion to increase water use efficiency and reduced sediment/nutrient transport to stream | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structures for implementation | Increase in available habitat and Protection from mechanical injury | 0.2 |  |  | 0.8 | 334.9 | Private | 175000 | Maybe - USDA RCPP
9 | Caribou Creek 05.5 Screening and Passage | 2027 |  | Caribou MSA | Caribou Creek | 3- Between CID and KRD | 46.9957 | -120.396 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Plan and design fish screen and fish passage for diversion of 1.6 CFS [Water RightS4-84505-J] for irrigation of 63 acres and stock water and potential on-farm sprinkler conversion to increase water use efficiency and reduced sediment/nutrient transport to stream | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structures for implementation | Increase in available habitat and Protection from mechanical injury | 0.4 |  |  | 1.6 | 628 | Private | 175000 | Maybe - USDA RCPP
10 | Caribou Creek 05.9 (Vantage Hwy Culvert) | 2027 |  | Caribou MSA | Caribou Creek | 3- Between CID and KRD | 46.9759 | -120.4188 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Plan and design fish passage for the culvert at Vantage Highway. This is a Kittitas County owned structure. | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structures for implementation | Increase in available habitat | 1.84 |  |  |  |  | County | 1200000 | Maybe - USDA RCPP
| Naneum MSA | [14 empty] | 4.96 | 1.35 | 880 | 62.7406 | 10119.9 |  | 6380000
1 | Naneum Creek 03.2 | 2022-2023 | 2027 | Naneum MSA | Naneum | 1 - EWC and downstream | 46.9705 | -120.4845 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Irrigation diversion structure (channel spanning concrete dam with check structures) that is unscreened and a barrier. Project will involve irrigation system upgrade (sprinklers) and possible consolidation with downstream diversion to efficiently screen and provide passage. | 175-Produce Design 165-Produce Environmental Compliance Documentation 85-Remove/Breach Fish Passage Barrier 184-Install Fish Passage Structure 208-Irrigation Infrastructure Construction or Replacement 47-Plant Vegetation 198-Maintain Vegetation | Installs compliant fish screen to prevent fish mortality and injury Corrects fish passage barrier to increase available habitat | Increase in available habitat and Protection from mechanical injury | 1.2 | 0.2 | 150 | 3 | 1037 | Private | 225000 | Yes - Salmon Recovery Funding Board
2 | Naneum 3.75 | 2026 | 2026-2027 | Naneum MSA | Naneum | 1 - EWC and downstream | 46.9779 | -120.4807 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | CMP culvert on a farm access road in Naneum Creek. Project will remove the culvert, install a 3 sided box culvert, and a woody debris structure. | 175-Produce Design and others | Corrects fish passage barrier to increase available habitat | Increase in available habitat | 0.65 | 0.1 | 250 |  |  | Private |  | Yes - Fish Barrier Removal Board
3 | Naneum Creek 04.4 (Ellensburg Water Company) | 2022-2026 | 2027-2028 | Naneum MSA | Naneum | 1 - EWC and downstream | 47.0057 | -120.4726 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Ellensburg Water Company intersection with Naneum Creek. Creek in culvert under canal. Project to place canal in siphon and restore streambed | 175-Produce Design 165-Produce Environmental Compliance Documentation 85-Remove/Breach Fish Passage Barrier 47-Plant Vegetation 198-Maintain Vegetation | Corrects fish passage barrier to increase available habitat | Increase in available habitat | 0.6 | 0.25 | 200 |  |  | Private | 850000 | Yes- Fish Barrier Removal Board and USDA RCPP
4 | Coleman Creek 04.8 and 05.22 Raap Diversion | 2023-2027 | 2027-2028 | Naneum MSA | Coleman Creek | 2 - Between EWC and CID | 46.9965 | -120.4623 | Mid-Columbia Summer Steelhead Spring Chinook Coho | juvenile/rearing | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Consolidation of two diversions to upper location and installation of fish screen and fish passage structures. | 175-Produce Design 165-Produce Environmental Compliance Documentation 184-Install Fish Passage Structure 208-Irrigation Infrastructure Construction or Replacement 47-Plant Vegetation 198-Maintain Vegetation | Installs compliant fish screen to prevent fish mortality and injury Corrects fish passage barrier to increase available habitat | Increase in available habitat and Protection from mechanical injury | 0.42 | 0.2 | 180 | 4 | 1522 | Private | 550000 | Maybe - USDA RCPP
5 | Nanuem Creek 05.0 - Three Diversions | 2027-2028 | 2028-2029 | Naneum MSA | Naneum | 2 - Between EWC and CID | 46.993813 46.996330 47.003413 | -120.472860 -120.471916 -120.472686 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Assess stream mile 5 on Naneum Creek to verify diversion locations and status. At least one has a fish screen installed in the early 2000's with NRCS funding. Others appear in adjudication, but no current verification if active. If so, address screen and passage for diversions. [Water Rights S4-84148-J, S4-84141-J,S4-84233-J, S4-84288-J] | 115- Produce Inventory or Assessment 175-Produce Design 165-Produce Environmental Compliance Documentation 85-Remove/Breach Fish Passage Barrier 184-Install Fish Passage Structure 208-Irrigation Infrastructure Construction or Replacement 47-Plant Vegetation 198-Maintain Vegetation | Installs compliant fish screen to prevent fish mortality and injury Corrects fish passage barrier to increase available habitat | Increase in available habitat and Protection from mechanical injury | 0.9 |  |  | 1.472 | 375.5 | Private | 180000 | Maybe - USDA RCPP
6 | Naneum Creek 05.9 (Cascade Irrigation District) | 2023-2024 |  | Naneum MSA | Naneum | 2 - Between EWC and CID | 47.0058 | -120.4728 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Cascade Irrigation District intersection with Naneum Creek. Designs for both a fish screen and fish passage at the site by installing a siphon for the canal to pass under the creek. | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structure for implementation | Increase in available habitat and Protection from mechanical injury | 0.1 |  |  | 17.52 | 916 | Irrigation District ROW | 1800000 | Yes - Salmon Recovery Funding Board for design
7 | Coleman Creek 05.63 Clerf Diversion | 2026-2028 |  | Naneum MSA | Coleman Creek | 3 - between CID and KRD | 47.0067 | -120.4542 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Plan and design fish screen and fish passage for diversion of 6 CFS [Water Right S4-84486-J, S4-84504-J,S4-84445-J,S4-84447- J,S4-84485-J]. This is the first diversion upstream of the Cascade Irrigation District intersection. | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structure | Increase in available habitat and Protection from mechanical injury | 0.2 |  |  | 6.55 | 2493.5 | Private | 180000
8 | Coleman Creek 06.24 - Diversion with 2 Culverts | 2026-2028 |  | Naneum MSA | Coleman Creek | 3 - between CID and KRD | 47.0146 | -120.4494 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Plan and design fish screen and fish passage for diversion of 3 CFS [Water Right S4-84525-J gravity diversion]. This diversion is located in area with high potential for riparian enhancement and that will be included in the planning process. | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structure | Increase in available habitat and Protection from mechanical injury | 0.61 |  |  | 1.96 | 687 | Private | 120000
9 | Nanuem Creek 06.0 | 2027 |  | Naneum MSA | Naneum | 3 - between CID and KRD | 47.0072 | -120.4736 | Mid-Columbia Summer Steelhead | juvenile/rearing/ spawning | Habitat Quantity - Anthropogenic Barriers Injury and Mortality - Mechanical Injury | Assess two small gravity diversions (0.2 and .0386 cfs) immediately upstream of Cascade Irrigation District intersection. Determine screening and passage solutions. [Water Rights S4-84128, S4-84134-J] | 175-Produce Design 165-Produce Environmental Compliance Documentation | Design compliant fish screen and fish passage structures for implementation | Increase in available habitat and Protection from mechanical injury | 0.43 |  |  | 0.2386 | 49.9 | Private | 150000